## Executive Summary
Main Street Collectibles — On-Page SEO Audit & Tracker
Live-site verification as of July 27, 2026 (mainstreetnewcanaan.com)
Page | Status | Key Issue
Home ( / ) | Partial | Title fixed. Meta description is bloated (226 chars, has leftover text). H1 is a hidden logo tag only, no visible keyword H1. Planned H2 sections (Shop by Category, Why Shop With Us, Visit Our Store) not built.
Shop/Catalog ( /collections/trading-card ) | Partial | Title + H1 fixed. Meta description has a text-duplication bug ("baBrowse oseball"). Planned H2 category sections not built.
Baseball ( /collections/baseball ) | Broken | URL returns 404 (collection unpublished, no products). None of the planned title/description/H1/H2 are live.
Contact ( /pages/contact ) | Partial | Title + description fixed and correct. No H1 tag exists on the page at all. Planned H2 sections not built.
Hours & Info ( /pages/hours-and-info ) | Partial | Title + description fixed. H1 live as "Hours and Info" instead of planned "Store Hours & Location". Planned H2 sections not built.
TCG / Pokémon | Not Yet Audited | Not checked in this pass.
Basketball / WNBA | Not Yet Audited | Not checked in this pass.
Football / NFL | Not Yet Audited | No dedicated page planned yet — pending client scope decision.
Hockey / NHL | Not Yet Audited | No dedicated page planned yet.
Merchandise (product template) | Not Yet Audited | Not checked in this pass.
About | Not Yet Audited | URL decision (/pages/info vs /pages/about) still needs confirmation.
Gift Cards | Not Yet Audited | Not checked in this pass.
Product page template | Not Yet Audited | Not checked in this pass.
Priority Fix List (in order)
1. Baseball collection is 404ing publicly — either add product(s) so the collection can be published, or intentionally unpublish/redirect it so it doesn't sit as a dead link in the sitemap.
2. Fix the corrupted Shop page meta description ("baBrowse oseball" text-duplication bug) — likely a copy/paste error in the Shopify SEO field.
3. Trim the Home page meta description back down to ~155-160 chars — it currently has extra trailing text pushing it to 226 chars, which Google will cut off mid-sentence.
4. Add a real visible H1 to the Contact page — it currently has none.
5. Align the Hours & Info H1 to "Store Hours & Location" (currently "Hours and Info").
6. Add a real, visible, keyword-rich H1 to Home (currently only a visually-hidden logo H1) and build out the three planned H2 content sections.
7. Build the four planned H2 category sections on the Shop page (Pokémon Cards / Sports Cards / Sealed Product / Graded & Vintage Singles).
8. Build the three planned H2 sections on Contact and on Hours & Info.
9. Audit and fix the remaining not-yet-checked pages (TCG/Pokémon, Basketball/WNBA, Merchandise, About, Gift Cards, product template) using the same method.

## Page Tracker
Page | URL | Meta Title (Planned) | Meta Title (Live) | Title Status | Meta Description (Planned) | Meta Description (Live) | Description Status | H1 (Planned) | H1 (Live) | H1 Status | H2/H3 (Planned) | H2 (Live) | H2 Status | Overall Status | Notes / Next Action
Home | / | Hobby Shop in New Canaan, CT ¦ Main Street Collectibles | Hobby Shop in New Canaan, CT ¦ Main Street Collectibles | Done | Your one-stop shop to buy and sell trading cards, sports cards & memorabilia. Visit us in-person or shop online: Pokémon, baseball, basketball cards + more. | Buy and sell trading cards, sports cards & memorabilia at our New Canaan, CT hobby shop. Shop online or in-person: Pokémon, baseball, basketball cards + more. New Canaan's premier destination for trading cards and collectibles (226 chars — too long, trim it) | Partial | Trading Cards & Sports Collectibles in New Canaan, CT | "Main Street Collectibles" (visually-hidden logo H1 only — no visible keyword H1 exists) | Not Started | Shop by Category (Pokemon/Baseball/Basketball/TCG); Why Shop With Us; Visit Our New Canaan Store | None of the planned sections exist. Only theme chrome (cart drawer, newsletter signup, search) | Not Started | Partial | Title is correct. Fix bloated meta description. Add a real content section with a visible H1, then add the 3 planned H2 sections.
Shop / Catalog | /collections/trading-card (redirected from /collections/online-store — note: singular "trading-card", plan said plural "trading-cards") | Trading Cards for Sale ¦ Main Street Collectibles New Canaan | Trading Cards for Sale ¦ Main Street Collectibles New Canaan | Done | Browse our trading card collection online or visit our hobby shop in New Canaan, CT. Pokémon, baseball & basketball cards, sealed boxes, graded singles! | BUG: "...Pokémon, baBrowse oseball & basketball cards..." — a text-duplication/copy-paste error has corrupted the word "baseball" in the live field. | Broken | Shop Trading & Sports Cards | Shop Trading & Sports Cards | Done | Pokemon Cards; Sports Cards (Baseball & Basketball); Sealed Product & Booster Boxes; Graded & Vintage Singles | None of the planned sections exist. Only theme chrome (cart drawer, filter drawer, newsletter, search) | Not Started | Partial | 301 redirect from old URL confirmed working. Fix the corrupted meta description immediately. Build the 4 category H2 sections. Confirm whether URL should be plural per original plan.
Baseball | /collections/baseball | Baseball Cards for Sale ¦ Main Street Collectibles, CT | 404 Not Found – Main Street Collectibles | Broken | Browse incredible baseball card collection online or visit our hobby shop in New Canaan, CT. Vintage packs, rookie cards, graded singles + more! | (none — page 404s) | Broken | Baseball Cards | Page not found | Broken | Vintage & Rookie Baseball Cards; Baseball Packs & Sealed Product; Sell Your Baseball Cards | (none — page 404s) | Broken | Broken | Collection is unpublished/empty (no products), so it 404s publicly. Either add product(s) and publish, or leave unpublished until inventory exists — but do not leave it linked/indexed as a live 404.
Contact | /pages/contact | Contact Main Street Collectibles ¦ New Canaan, CT | Contact Main Street Collectibles ¦ New Canaan, CT | Done | Come visit our hobby shop in New Canaan, CT! Main Street Collectibles address, hours, directions, and info on how to buy or sell cards. | Come visit our hobby shop in New Canaan, CT! Main Street Collectibles address, hours, directions, and info on how to buy or sell cards. | Done | Contact Main Street Collectibles | (none — no H1 tag exists anywhere on the page) | Not Started | Visit Our Store; Sell Your Cards; Store Hours & Directions | None of the planned sections exist. Only theme chrome (cart drawer, newsletter, search) | Not Started | Partial | Title and description are correct and live. Add the missing H1 and build the 3 planned H2 sections.
Hours & Info | /pages/hours-and-info | Store Hours & Location ¦ Main Street Collectibles New Canaan | Store Hours & Location ¦ Main Street Collectibles New Canaan | Done | Come visit our hobby shop in New Canaan, CT! Main Street Collectibles hours, location, and directions. | Come visit our hobby shop in New Canaan, CT! Main Street Collectibles hours, location, and directions. | Done | Store Hours & Location | Hours and Info | Partial | Today's Hours; Directions & Parking; Trade Nights / Events (if applicable) | None of the planned sections exist. Only theme chrome (cart drawer, newsletter, search) | Not Started | Partial | Title and description are correct and live. Update H1 text to exactly match the plan, then build the 3 planned H2 sections.
TCG / Pokémon | /collections/tcg-card | Pokémon Cards for Sale ¦ Main Street Collectibles New Canaan | Not yet audited | Not Yet Audited | Browse our incredible collection online or visit our hobby shop in New Canaan, CT and consult with our expert team. Rare singles, packs, sealed product + more! | Not yet audited | Not Yet Audited | Pokémon TCG Cards | Not yet audited | Not Yet Audited | Pokemon Singles & Sealed Product; Vintage & 1st Edition Pokemon; Other TCG (MTG, Yu-Gi-Oh & More) | Not yet audited | Not Yet Audited | Not Yet Audited | Check this page live using the same method as the 5 pages above.
Basketball / WNBA | /collections/basketball, /collections/wnba | No dedicated title — folded into Shop page (needs decision) | Not yet audited | Not Yet Audited | No dedicated description — covered by Shop page for now (needs decision) | Not yet audited | Not Yet Audited | N/A — not a standalone page at this time | Not yet audited | Not Yet Audited | N/A | Not yet audited | Not Yet Audited | Not Yet Audited | These URLs already exist live — decide whether to give them unique metadata or canonicalize/noindex them to the Shop page so they don't sit as duplicate/thin content.
Football / NFL | No dedicated collection — surfaces via Shop only | No dedicated title — pending client scope decision | N/A | Not Yet Audited | Covered by Shop page for now | N/A | Not Yet Audited | N/A — not a standalone page at this time | N/A | Not Yet Audited | N/A | N/A | Not Yet Audited | Not Yet Audited | New finding — needs client decision on whether this becomes a standalone collection page.
Hockey / NHL | No dedicated collection — surfaces via Shop only | No dedicated title — folded into Shop page | N/A | Not Yet Audited | Covered by Shop page for now | N/A | Not Yet Audited | N/A — not a standalone page at this time | N/A | Not Yet Audited | N/A | N/A | Not Yet Audited | Not Yet Audited | New finding — needs client decision on whether this becomes a standalone collection page.
Merchandise (template) | /products/msc-trucker-hat (example) | [Item Name] ¦ Main Street Collectibles, New Canaan | Not yet audited | Not Yet Audited | Shop Main Street Collectibles branded merchandise, including [item name] and more! Shop online or visit our hobby shop in New Canaan, CT. | Not yet audited | Not Yet Audited | [Item Name] | Not yet audited | Not Yet Audited | N/A — standard product page, no card-specific sections needed | Not yet audited | Not Yet Audited | Not Yet Audited | Note: this exact item (MSC Trucker Hat) was found mixed into the Shop/Catalog collection grid during this audit — confirm it's tagged/categorized correctly and not duplicated across collections.
About | /pages/info (CONFIRM: proposed /pages/about) | About Main Street Collectibles ¦ New Canaan CT Card Shop | Not yet audited | Not Yet Audited | Main Street Collectibles is a hobby shop in New Canaan, CT owned by passionate experts in trading cards and sports memorabilia. Read our story. | Not yet audited | Not Yet Audited | About Main Street Collectibles | Not yet audited | Not Yet Audited | Our Story; What We Buy & Sell; Why Collectors Shop With Us | Not yet audited | Not Yet Audited | Not Yet Audited | URL decision still open. If moving to /pages/about, set up a 301 redirect from /pages/info first, same as was done for the Shop page.
Gift Cards | /products/msc-gift-card | Gift Cards ¦ Main Street Collectibles New Canaan | Not yet audited | Not Yet Audited | The perfect gift for anyone passionate about the hobby. We sell trading cards, sports cards & memorabilia. Shop online or visit our store in New Canaan, CT. | Not yet audited | Not Yet Audited | Main Street Collectibles Gift Cards | Not yet audited | Not Yet Audited | How Gift Cards Work; Redeeming In-Store or Online | Not yet audited | Not Yet Audited | Not Yet Audited | Check this page live using the same method as the 5 pages above.
Product page (template) | /products/[handle] | [Year] [Set] [Card Name] [Grade/Edition] ¦ Main Street Collectibles | Not yet audited | Not Yet Audited | Buy the [Card Name], graded [condition/grade] with [key attribute]. In stock at Main Street Collectibles, New Canaan CT. [Price if available]. | Not yet audited | Not Yet Audited | [Year] [Set] [Card Name] [Grade/Edition] | Not yet audited | Not Yet Audited | Card Details; Why Choose This Card; Authenticity & Condition; FAQ | Not yet audited | Not Yet Audited | Not Yet Audited | Needs a bulk-template approach (metafields/CSV import or SEO app) since this applies per-product, not a one-off manual edit.