# Main Street Collectibles

Shopify Developer Audit & Scope Estimate

Site: https://mainstreetnewcanaan.com/
Audit date: July 14, 2026
Audit method: Live storefront review (theme, navigation, collections, products, apps, policies)

# Executive Summary

Main Street Collectibles is a live Shopify store on the Horizon theme with 265 products, a working consultation/selling product, and Easy Appointment Booking (Servicify) installed. The storefront is functional but still reflects initial setup: pickup is not configured at checkout, navigation and collections are misaligned, catalog quality is uneven, and the selling workflow lacks a structured pre-appointment intake form.

Estimated effort for the full scope below: 55–75 developer hours (approximately 7–10 working days), plus client review cycles. Admin access is required to complete pickup configuration, app settings, and theme changes.

# Current State Assessment

## Theme

Shopify Horizon theme (theme store ID 2481), default configuration with minimal customization.

Homepage features 4 products from the ONLINE STORE collection; no hero messaging or sell/pickup CTAs.

Brand assets present (logo, favicon, Instagram link). Inter font, standard color scheme.

Footer includes Facebook, Instagram, and policy links.

## Navigation

Home → /

Sell your Cards → /products/consultation (selling consultation product — not a dedicated intake page)

Store Pickup → /collections/online-store (15 shippable sealed products — NOT pickup inventory)

Gift cards → /products/msc-gift-card (collection /collections/gift-cards is empty)

Reviews → External Google Maps reviews URL (leaves site)

Hours and Info → /pages/hours-and-info

Contact → /pages/contact (basic Shopify contact form)

Critical: “Store Pickup” nav points to the wrong collection. The full catalog (265 items) displays as “Store Pickup Items” at /collections/all but is not linked from nav.

## Collections & Catalog

265 total products; 15 in ONLINE STORE (sealed/shippable); ~250 graded singles and inventory items not in ONLINE STORE.

Empty or unused collections: Baseball, Basketball, WNBA, GIFT CARDS (0 products).

66 products missing images; 231 products missing descriptions.

263 of 265 variants marked requires_shipping: true (pickup not product-level ready).

## Settings & Configuration

Custom domain active; Shopify Payments enabled; Google Analytics / GTM installed.

Shipping policy returns 404 — not configured.

Sitemap (/sitemap.xml) returns 500 error.

Apple Pay / checkout metadata shows shippingType: "shipping" only — no local pickup exposed.

Store address referenced correctly in announcement bar: 102 Main Street, New Canaan CT 06840.

## Pickup Flow

Local pickup is NOT live. Checkout is shipping-only from storefront signals.

No dedicated pickup collection handle; /collections/all titled “Store Pickup Items” but functions as the full catalog.

ONLINE STORE collection (15 items) appears intended for shipped sealed product, separate from in-store pickup inventory.

Pickup location (102 Main Street) referenced on site but not configured as a Shopify pickup point in checkout.

## Buying / Selling Workflow

15 Minute Trading Card Consultation product exists with thorough selling copy ($0.00).

Easy Appointment Booking (Servicify / digital-appointments) installed; booking widget renders on consultation product.

App embed also loads on standard product pages — should be scoped to consultation/selling only.

No structured intake form for item details (card type, quantity, graded/raw, photos, estimated value) before appointment.

Workflow today: nav → consultation product → book appointment. No data capture for buyer inventory ahead of visit.

## Schema & Data Requirements (Buying Intake)

Recommended intake fields for buyer workflow:

Contact: name, email, phone

Appointment preference / link to Servicify booking

Collection size (single items vs. small lot vs. large collection)

Card details: sport/category, player, year, set, card number

Condition: raw vs. graded (with grade if applicable)

Estimated quantity and approximate value range

Photo upload (front/back or stack photo)

Notes: rookies, autos, numbered, vintage flags

Acknowledgment of buying criteria (graded 8+, ~$20+ value, etc.)

Data should flow to merchant (email notification, Shopify customer record, or Servicify appointment notes) and be visible to staff before the 15-minute consultation.

# Key Issues Found

| Issue | Severity |
| --- | --- |
| Local pickup not configured in Shopify admin/checkout | High |
| Store Pickup nav links to ONLINE STORE (wrong collection) | High |
| No buying intake form; appointment booking only | High |
| Servicify app embed on all product pages | Medium |
| 66 products without images | Medium |
| 231 products without descriptions | Medium |
| Shipping policy missing (404) | Medium |
| Sitemap error (500) | Low |
| Empty sport/gift card collections in catalog | Low |
| Info page is logo-only placeholder | Low |
| Gift cards nav → product; collection empty | Low |

# Subtask 1: In-Store Pickup Configuration

Scope: Set up collections as shoppable for in-store pickup, configure pickup for key collections, build purchase/pickup flow, set pickup location (102 Main Street), test checkout, document for client.

## Work Required

Enable Shopify local pickup at 102 Main Street (Settings → Locations → Pickup in store).

Define fulfillment strategy: ONLINE STORE = ship; pickup-eligible inventory = local pickup only (or pickup + optional ship if needed).

Create or retitle dedicated Store Pickup collection(s) by category (e.g., graded singles, Pokémon, sports).

Assign ~250 pickup-eligible products to correct collections; tag products for fulfillment rules.

Configure shipping/pickup profiles so checkout offers “Pickup at 102 Main Street” for eligible items.

Fix navigation: Store Pickup → correct collection(s), not ONLINE STORE.

Add pickup messaging on collection and product pages (ready in X hours, bring ID, etc.).

End-to-end test: add pickup item → checkout → select pickup → order confirmation.

Write client-facing pickup documentation (how to buy, when to collect, mixed cart rules).

## Estimate

| Admin setup (location, pickup, shipping profiles) | 4–6 hrs |
| --- | --- |
| Collection structure & product assignment | 5–8 hrs |
| Nav, PDP/collection UX & messaging | 2–4 hrs |
| Checkout testing & edge cases | 3–4 hrs |
| Client documentation | 1–2 hrs |
| Subtotal | 15–24 hrs |

## Dependencies & Risks

Requires Shopify admin access and POS/location already set for 102 Main Street.

Mixed carts (ship + pickup) need a clear business rule to avoid checkout confusion.

Large catalog (265 SKUs) — bulk tagging/collection rules recommended over manual one-by-one.

# Subtask 2: Store Cleanup

Scope: Tidy theme, navigation, and settings from initial setup. Fix nav, clean settings, ensure storefront is presentable, fix broken elements.

## Work Required

Reorganize navigation: correct pickup link, add Shop Online if desired, fix Reviews (on-site or labeled external).

Homepage: hero section, featured collections, sell-cards CTA, store hours/location block.

Remove or hide empty collections (Baseball, Basketball, WNBA, empty Gift Cards).

Resolve gift card path (product vs. collection consistency).

Create shipping policy; update refund policy for pickup orders if needed.

Investigate and fix sitemap 500 error.

Scope Servicify app embed to selling/consultation templates only.

Product presentation pass: placeholder images for 66 missing images (client assets needed for final).

Theme settings: announcement bar, footer, typography consistency.

Full storefront QA (mobile + desktop).

## Estimate

| Navigation & information architecture | 3–5 hrs |
| --- | --- |
| Homepage & theme polish | 4–6 hrs |
| Collection/catalog cleanup | 3–4 hrs |
| Policies, app embed fix, sitemap | 2–4 hrs |
| QA & broken-element fixes | 3–5 hrs |
| Subtotal | 15–24 hrs |

## Dependencies & Risks

Product photography/content for 66+ items depends on client turnaround.

Some cleanup overlaps with pickup work (nav, collections) — coordinate to avoid duplicate effort.

# Subtask 3: Buying Intake Form

Scope: Build customer selling intake form aligned to existing buying workflow. Integrate with Easy Appointment Booking (Servicify). Build form → collect item details → integrate appointment booking → test → client review.

## Work Required

Confirm required fields with client (use schema list above as starting point).

Build intake form (Shopify Forms, custom theme section, or form app — recommend based on photo upload needs).

Create dedicated “Sell Your Cards” page with form → booking flow (form first, then schedule).

Integrate with Servicify: pass intake data to appointment notes, customer metafields, or email notification.

Update consultation product page to reflect two-step flow (intake + book).

Configure staff notifications (email/Shopify Flow) with submitted item details.

Test full journey: form submit → appointment book → merchant receives data.

Client review and iteration on copy/fields.

## Estimate

| Requirements & form design | 3–4 hrs |
| --- | --- |
| Form build (fields, validation, photo upload) | 5–8 hrs |
| Servicify integration & data routing | 5–8 hrs |
| Sell page UX & consultation product updates | 3–4 hrs |
| Testing & client review cycle | 4–6 hrs |
| Subtotal | 20–30 hrs |

## Dependencies & Risks

Servicify custom-field support limits may require Shopify Forms + manual staff review or Zapier/Flow middleware.

Photo uploads may need a form app (e.g., HulkApps, Powerful Form Builder) if native Shopify Forms is insufficient.

Client must approve field list and notification workflow before build is final.

# Full Scope Summary

| Subtask | Hours (Low–High) | Notes |
| --- | --- | --- |
| In-Store Pickup Configuration | 15–24 hrs | Admin + catalog assignment heavy |
| Store Cleanup | 15–24 hrs | Partial overlap with pickup nav/collections |
| Buying Intake Form | 20–30 hrs | Servicify integration is main variable |
| TOTAL (sequential) | 50–78 hrs | ~7–10 working days |

Recommended approach: Run Store Cleanup and Pickup Configuration in parallel where possible (shared nav/collection work). Begin Buying Intake Form after client confirms field requirements. Add 1–2 days buffer for client review on each subtask.

# Recommended Execution Order

1. Store Cleanup (nav, policies, app embed) — quick wins, improves live site immediately.

2. In-Store Pickup Configuration — highest revenue impact for local customers.

3. Buying Intake Form — depends on client field approval and Servicify integration testing.

# Access Required

Shopify admin (staff or collaborator access)

Theme editor access (Horizon)

Easy Appointment Booking / Servicify app admin

Client input on pickup vs. ship rules and intake form fields

Product images/descriptions for catalog gaps (client-provided)

# Out of Scope (This Audit)

POS hardware setup

Inventory migration or bulk import

Custom theme development beyond Horizon settings

SEO/marketing campaigns

Payment method changes

— End of Report —