# Project Report & Time Estimate

EXP School Profiles
Replace PDFs with CPT + Filters

Prepared: July 09, 2026
Reference: ClickUp Task #869e0yffm
Pilot Country: New Zealand
Timeline: 5 Development Days + 1 Testing Day
Environment: DEV

# 1. Executive Summary

This report outlines the scope, technical approach, deliverables, and a compressed 6-day delivery schedule for replacing EXP's downloadable school PDFs with a reusable WordPress-based school directory. The solution uses Custom Post Types (CPT), Advanced Custom Fields (ACF), FacetWP filtering, and WordPress Taxonomies — reusing the Müller project architecture to meet an accelerated timeline.

| Metric | Value |
| --- | --- |
| Development | 5 days (40 hours) |
| Testing & QA | 1 day (8 hours) |
| Total Project Duration | 6 days (48 hours) |
| Developer Allocation | 1 developer, full-time (8 hrs/day) |
| Pilot Country | New Zealand |
| Future Reuse | All other countries |

Schedule at a Glance:

| Day | Focus | Hours |
| --- | --- | --- |
| Day 1 | Discovery, setup & data model (CPT + taxonomies) | 8 |
| Day 2 | ACF field groups & school profile template | 8 |
| Day 3 | Region overview, filter page & country page CTAs | 8 |
| Day 4 | FacetWP integration & URL preselection | 8 |
| Day 5 | NZ content migration & reusability setup | 8 |
| Day 6 | Testing, QA, bug fixes & handover | 8 |
|  | TOTAL | 48 |

# 2. Background & Problem Statement

EXP currently publishes school information as downloadable PDFs (e.g. USA Choice schools). Every content update requires editing and re-uploading a PDF, which is slow and not searchable.

Current pain points:

Content updates require manual PDF editing and re-uploading

No searchable, filterable school directory on the website

No CMS-level control for non-technical staff

## 2.1 Project Goal

School Profile Custom Post Type (CPT)

Filter page using FacetWP

Region overview pages

Integration with existing country pages

Pilot country: New Zealand. Structure reusable for all other countries.

# 3. Technical Stack & Architecture

| Component | Purpose |
| --- | --- |
| WordPress | Core CMS platform |
| Custom Post Type: School Profiles | Individual school pages replacing PDFs |
| ACF (Advanced Custom Fields) | Display-only content (descriptions, images, fees) |
| FacetWP | Frontend filtering and school listing |
| WordPress Taxonomies | Filterable values editable by EXP (regions, interests, etc.) |

## 3.1 Critical Design Rule

User-extendable values (regions, interests, school types) = Taxonomies. Pure display information = ACF fields.

# 4. Page Structure & User Flows

## 4.1 Country Page (Minor Update)

Example: /schueleraustausch-weltweit/neuseeland/

CTA: "Choose School Directly" → Filter page (country preselected)

CTA: "Choose Region" → Region overview page

## 4.2 Region Overview Page (New)

Shows major regions (NZ: North Island, South Island)

Region selection opens filter page with country + region preselected

## 4.3 Filter Page (New)

FacetWP filters + school listing

Supports entry with no filters, country only, or country + region

EXP can add/remove/adjust filters independently

## 4.4 School Profile — CPT Single (New)

Each school = own WordPress page (replaces PDF)

Taxonomy filter values visible on profile page

## 4.5 User Flows

Option 1:

Country Page → Choose School Directly → Filter Page → School Profile

Option 2:

Country Page → Choose Region → Region Overview → Filter Page → School Profile

# 5. Filter Categories & Data Structure

## 5.1 Required Filters (Taxonomies)

| Filter | Type | Notes |
| --- | --- | --- |
| Country | Taxonomy | Editable by EXP |
| Region | Taxonomy | Hierarchical under country |
| City | Taxonomy | Editable by EXP |
| Interests | Taxonomy | Multi-select |

## 5.2 Optional Filters

| Filter | Type | Status |
| --- | --- | --- |
| Language Offering | Taxonomy | If time permits on Day 4 |
| School Type (High School, Private, Boarding) | Taxonomy | If time permits on Day 4 |
| School Gender | Taxonomy | Pending client approval |
| Academies / Focus Areas | Taxonomy | Pending client approval |

## 5.3 ACF Fields (Display-Only)

| Group | Fields |
| --- | --- |
| Introduction | Intro text, school description |
| Media | Images, gallery |
| Practical | Accommodation, activities |
| Financial | Tuition / fees |
| Downloads | File attachments (if required) |

# 6. Deliverables

| # | Deliverable | Delivery Day |
| --- | --- | --- |
| D1 | School Profile CPT + taxonomies | Day 1 |
| D2 | ACF field group | Day 2 |
| D3 | School profile single template | Day 2 |
| D4 | Region overview template | Day 3 |
| D5 | Filter page template | Day 3 |
| D6 | Country page CTA integration | Day 3 |
| D7 | FacetWP integration + URL preselection | Day 4 |
| D8 | NZ pilot content entered | Day 5 |
| D9 | Reusable multi-country architecture | Day 5 |
| D10 | Tested, QA-approved & handed over | Day 6 |

# 7. Detailed Schedule — 5 Development Days + 1 Testing Day

This accelerated schedule is achievable by reusing Müller project patterns, limiting the NZ pilot to core schools, and deferring optional filters to a follow-up if needed.

## Day 1 — Discovery, Setup & Data Model (8 hours)

| ID | Task | Hours | Notes |
| --- | --- | --- | --- |
| 1.1 | Review Müller reference & reuse existing code patterns | 1.5 | CPT/taxonomy boilerplate |
| 1.2 | DEV environment setup, plugin verification (ACF, FacetWP) | 1.0 |  |
| 1.3 | Register School Profile CPT | 1.5 | Rewrite rules, admin columns |
| 1.4 | Register taxonomies: Country, Region, City, Interests | 3.0 | All required filters |
| 1.5 | Create NZ taxonomy terms (regions, cities, interests) | 1.0 | North/South Island setup |

Day 1 Subtotal: 8.0 hours

## Day 2 — ACF Fields & School Profile Template (8 hours)

| ID | Task | Hours | Notes |
| --- | --- | --- | --- |
| 2.1 | Map PDF fields to ACF structure | 1.5 | Use existing PDF as reference |
| 2.2 | Build ACF field group (content, media, fees, downloads) | 3.0 | Core fields only |
| 2.3 | School profile single page template | 3.0 | Match client reference layout |
| 2.4 | Display taxonomy terms on school profile | 0.5 | Show active filter values |

Day 2 Subtotal: 8.0 hours

## Day 3 — Page Templates & Country Integration (8 hours)

| ID | Task | Hours | Notes |
| --- | --- | --- | --- |
| 3.1 | Region overview page template | 2.5 | Region cards with deep-links |
| 3.2 | Filter page template shell | 1.5 | Layout wrapper for FacetWP |
| 3.3 | Country page CTA buttons (2 buttons) | 1.5 | Choose School / Choose Region |
| 3.4 | Responsive styling for all new templates | 2.0 | Mobile + desktop |
| 3.5 | Internal page linking & routing verification | 0.5 | All user flow paths |

Day 3 Subtotal: 8.0 hours

## Day 4 — FacetWP Integration & URL Preselection (8 hours)

| ID | Task | Hours | Notes |
| --- | --- | --- | --- |
| 4.1 | Configure FacetWP facets (Country, Region, City, Interests) | 3.0 | Required filters |
| 4.2 | School listing template with result cards | 2.0 | Links to CPT singles |
| 4.3 | URL preselection: country only | 1.5 | From country page CTA |
| 4.4 | URL preselection: country + region | 1.5 | From region overview |

Day 4 Subtotal: 8.0 hours

## Day 5 — Content Migration & Reusability (8 hours)

| ID | Task | Hours | Notes |
| --- | --- | --- | --- |
| 5.1 | Enter/migrate NZ school profiles (pilot batch) | 5.0 | ~10 core schools for launch |
| 5.2 | Assign taxonomy terms to all NZ schools | 1.0 | Filter assignments |
| 5.3 | Parameterize templates for future countries | 1.5 | No hardcoded NZ logic |
| 5.4 | Quick content review against source PDFs | 0.5 | Spot-check accuracy |

Day 5 Subtotal: 8.0 hours

## Day 6 — Testing, QA & Handover (8 hours)

| ID | Task | Hours | Notes |
| --- | --- | --- | --- |
| 6.1 | Functional testing — both user flows (Option 1 & 2) | 2.0 | End-to-end paths |
| 6.2 | FacetWP filter combination & edge case testing | 1.5 | Empty results, reset, multi-filter |
| 6.3 | Cross-browser & responsive testing | 1.5 | Chrome, Firefox, Safari, mobile |
| 6.4 | UAT support & bug fixes | 2.0 | Client feedback iteration |
| 6.5 | CMS handover documentation & brief training | 1.0 | How EXP manages schools/filters |

Day 6 Subtotal: 8.0 hours

## 7.1 Schedule Summary

| Day | Phase | Type | Hours |
| --- | --- | --- | --- |
| Day 1 | Discovery, Setup & Data Model | Development | 8.0 |
| Day 2 | ACF Fields & School Profile Template | Development | 8.0 |
| Day 3 | Page Templates & Country Integration | Development | 8.0 |
| Day 4 | FacetWP Integration & URL Preselection | Development | 8.0 |
| Day 5 | Content Migration & Reusability | Development | 8.0 |
| Day 6 | Testing, QA & Handover | Testing | 8.0 |
|  | GRAND TOTAL |  | 48.0 |

| Category | Days | Hours |
| --- | --- | --- |
| Development (Days 1–5) | 5 | 40 |
| Testing & QA (Day 6) | 1 | 8 |
| Total | 6 | 48 |

# 8. Assumptions for 6-Day Delivery

Müller project code/patterns are directly reusable — no greenfield architecture.

ACF Pro and FacetWP are already installed and licensed in DEV.

Required filters only (Country, Region, City, Interests) — optional filters deferred.

NZ pilot limited to ~10 core schools at launch; remaining schools added by EXP post-handover.

Filter definitions from Excel file are finalized before Day 1.

School profile reference layout is approved — no design iteration during build.

Country page accepts CTA buttons without structural theme changes.

Client content (school data) is provided before Day 5.

One experienced WordPress developer, full-time, no context switching.

No scope changes during the 6-day window.

## 8.1 Deferred to Post-Launch (if needed)

Optional filters (Language Offering, School Type, School Gender, Academies)

Remaining NZ schools beyond the initial ~10

Production deployment (DEV delivery within 6 days)

SEO/redirect strategy for old PDF URLs

Multilingual / WPML integration

# 9. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Scope creep during 6-day window | High | Lock scope on Day 1; defer extras to Phase 2 |
| Müller code not fully reusable | High | Audit reuse on Day 1 morning; adjust Day 2–3 if needed |
| Client content not ready by Day 5 | Medium | Use placeholder content; EXP completes post-handover |
| FacetWP theme conflicts | Medium | Test integration early on Day 4 morning |
| More than 10 NZ schools required at launch | Low | Budget 0.5h per extra school or defer |

# 10. References

ClickUp Task: https://app.clickup.com/t/4601471/869e0yffm

Current PDF Example: experiment-ev.de/wp-content/uploads/2025...

Reference Implementation: Kulturwerke Deutschland — Kanada Öffentlich Schulwahl

NZ Schools Reference: DoIT Education — Unsere Schulen in Neuseeland

School Profile Layout: experiment-ev.de/schueleraustausch/schul...

Filter Source of Truth: Schulprofile-filter Excel file (AG_English.xlsx)

— End of Report —